## Roadmap Template
GANTT DİYAGRAMI
Proje İsmi: Artırılmış Gerçeklik İle Gökyüzünde Matematik Avı
| Görev İsimleri | Başlangıç (Tarih) | Son (Tarih) | Gün Sayısı
| Proje Planlanması ve Kapsam Raporu | 2024-10-05 | 2024-10-07 | 2
| Unity ve Vuforia Kurulumu ve Ayarları | 2024-10-07 | 2024-10-09 | 2
| Use-Case Diyagramının Oluşturulması | 2024-10-09 | 2024-10-12 | 3
| Activity-FlawC Diyagramının Oluşturulması | 2024-10-12 | 2024-10-17 | 5
| Class Diyagramının Oluşturulması | 2024-10-17 | 2024-10-19 | 2
| Mockup Planlanması ve Tasarlanması | 2024-10-19 | 2024-10-21 | 2
| Targetların oluşturulması | 2024-10-21 | 2024-10-22 | 1
| Unity Componentlerinin Oluşturulması | 2024-10-22 | 2024-10-24 | 2
| Ekran Tasarımı | 2024-10-24 | 2024-10-30 | 6
| Oyun Aşamalarının Tasarlanması | 2024-10-30 | 2024-11-05 | 6
| Butonların Eklenmesi | 2024-11-05 | 2024-11-11 | 6
| Sanal ve Fiziki Çalışabilirlik Test | 2024-11-11 | 2024-11-14 | 3
| Farklı Ortamlara Uyumluluk Testi | 2024-11-14 | 2024-11-24 | 10
| Modelin Doğruluğu ve Kullanılabilirlik Testi | 2024-11-24 | 2024-12-01 | 7
| Dağıtım ve Bakım İşlemleri | 2024-12-01 | 2024-12-08 | 7

## How To Use This Template
Introduction
Use this template to help you plan projects! When you update columns B, C, & D in the other tab your gantt chart will automatically update.
Of course, if you need to manage your projects online, in real-time, click the link to the right-----> where you can start your 30-day Free Trial!